## Form
1. This form is intended for all projects that meet the Recurrent Expenditure Assurance Framework (REAF) Mandatory Registration Criteria.
2. Delivery Agencies must register and conduct a self-Risk Assessment using this form to determine a preliminary Project Tier and proposed Assurance Plan.
3. Please email completed forms or enquires to gateway@treasury.nsw.gov.au
For further information, please refer to: | Recurrent Expenditure Assurance Framework
General
Project Name: | Please enter | Program: |  |  | Please enter if applicable
Lead Sponsor Agency: | Please enter | Stage at time of Project Registration: |  |  | - Please select -
Lead Delivery Agency: | Please enter | Registration Type: |  |  | - Please select -
Lead Responsible Minister: | Please enter | Proposal discussed with NSW Treasury? |  |  | - Please select -
|  | Treasury Policy and Budget Analyst Name: |  |  | Please enter name, role and team if applicable
|  | Type of Recurrent Expenditure: |  |  | - Please select -
Project Details
Description: | Please enter short description of the project. (2000 characters) | Project Governance |  |  | Please enter summary of the project governance (3000 characters)
Problem / Service Need | Please enter summary of the identified problem or service need. (1000 characters) | Key Project Milestones: |  |  | Please enter key project milestones (eg. Funding approval, Project Commissioning, Project Operationalisation) with estimated dates. (10,000 characters)
Objectives: | Please enter summary of project objectives and expected outcomes and benefits, in point form. The outcome and benefits ought to be related to documented state significant outcomes or service delivery outcomes. (3000 characters)
Project Stakeholder
Project Sponsor Name: | Please enter | SRO Name: |  | Please enter
Project Sponsor Email: | Please enter | SRO Email: |  | Please enter
Project Financials
Estimated Total Cost ($m) | Please enter ETC
Funding Source: | - Please select -
Funding Approval Status: | - Please select -
Funding Conditions: | Please enter conditions on the provisions of funding
ETC Band ($m):
Is ETC in any one year greater than $50M | - Please select -
Agency Self-risk Assessment
Risk Assessment Criteria | Agency Rating | Risk Score | Agency Rationale
Government Priority (15%) | - Please select - | - | Please enter
Interface Complexity (15%) | - Please select - | - | Please enter
Procurement Complexity (20%) | - Please select - | - | Please enter
Agency Capability (20%) | - Please select - | - | Please enter
Criticality of Service (15%) | - Please select - | - | Please enter
Implementation Complexity (15%) | - Please select - | - | Please enter
| Total Weighted Score | -
| Corresponding Risk Range | -
| Preliminary Project Tier (Estimated Total Cost + Ratings must be completed) | -
| Do you agree with the Preliminary Project Tier rating? |  | - Please select -
| If No, please nominate Project Tier and provide rationale |  | - Please select -
Please enter rationale
Agency's Proposed Assurance Plan:
Please see the mandatory Gateway Review requirements in Appendix 2. Please propose alternative Assurance Plan with rationale if applicable.
Gates | Agency Nomination | Agency comments / rationale
Gate 1 - Preliminary Business Case | - Please select - | Please enter any comments / rationale
Gate 2 - Full Business Case | - Please select -
Gate 3 - Pre-Execution | - Please select -
Gate 4 - Tender Evaluation | - Please select -
Gate 5 - Pre-Commissioning | - Please select -
Gate 6 - Post-Implementation | - Please select -
Proposed Health Checks | - Please select -
REAF Project Risk Assessment submission |  | REAF Project Risk Assessment approval
Please submit in accordance with your Delivery Agency's policy and delegations |  | Please approve in accordance with your Delivery Agency's policy and delegations
Submitted by: | Please enter full name | Approved by: |  | Please enter full name
Role: | Please enter | Role: |  | Please enter
Contact number: | Please enter | Contact number: |  | Please enter
Email address: | Please enter | Email address: |  | Please enter
|  | Date approved: |  | Please enter
REAF Risk Assessment Tool

## Appendix 1
Risk 1: Government Priority
Criteria and Weighting | Priority and Risk Level | Score | Evaluation Questions
Government priority: 15% The level and timing of project priority, where: • The level of priority for a project is specifically mandated (or mandated through Ministerial authority) in documents such as the NSW Budget, Premier’s Priorities, State Priorities, State Infrastructure Strategy, Election Commitment, or • The project is a direct enabler of a mandated priority project • The project is a response to new legislative requirements as a result of changes in law • Priority also depends on whether the timing of the project is within or outside the Forward Estimates. | Very High Government priority Priority Government project, and project will be fully operational within 12 months | 5 | Government Priority indicators: • Has the project been specifically mandated in the NSW Budget? • Has the project been specifically mandated in the Premier's Priorities? • Is the project linked to a project specifically mandated in any Government endorsed whole of Government plan, for example, the State Infrastructure Strategy? • Is the project an election commitment? • Is the project a response to a legislative change or to support a legislated Government objective • Is the project an enabler of a mandated priority project? • Has there been a Ministerial announcement regarding the project? • Has the project received significant regional or state-wide media coverage? • Is the project a strategic priority for Government? • Is the project a strategic priority for the agency or department? • Does accountability for the project reside with Cabinet, a Cabinet Committee, or a Minister? Project Timing indicators: • Has planning or implementation of the project already commenced? • Will the project be fully operational within 12 months? • Will the project be fully operational within the forward estimates period?
| High Government priority Priority Government project, and project will be fully operational within the next 1-2 years of the forward estimates period | 4
| Medium Government priority Priority Government project, and project will be fully operational within the next 3-4 years of the forward estimates period | 3
| Low Government priority Priority Government project, and project will be commenced within the forward estimates period | 2
| Very Low Government Priority Agency priority in Agency Strategic Plan over the next 10 years | 1
| Extremely Low Government priority Not a documented Government or agency priority | 0
Risk 2: Interface Complexity
Criteria and Weighting | Priority and Risk Level | Score | Evaluation Questions
Interface complexity: 15% The extent to which the project or program’s success will depend on the management of complex dependencies with other: • Institutions – certain bodies are contributing to the funding of the project or will be given operational responsibility. • Projects or services – there are fundamental interdependencies with other projects or services that will directly influence the scope and cost of the project. | Very high interface complexity risk Extensive interface and/or interdependence with other entities, projects, programs, or services | 5 | Interface Complexity indicators: • Are other entities contributing to the funding of the project? • Will other entities be given full or partial operational responsibility for the project? • Are there other projects, program or services that will directly influence the scope and cost of the project? • Does the project involve multi-agency delivery? • Are the anticipated project benefits dependent on another project, program or service? • Will the anticipated benefits be realised by any entity other than the Delivery Agency? • Does the project involve significant integration (IT or otherwise) with other projects, programs, or services? • Will members of the public be directly impacted by this project? • Will the private sector be directly impacted by this project? • Will the public sector (outside of the Delivery Agency) be directly impacted by this project? • Will the project involve external delivery partners?
| High interface complexity risk Frequent interface and/or interdependency with other entities, projects, programs, or services | 4
| Medium interface complexity risk Some interface and/or interdependency with other entities, projects, programs, or services | 3
| Low interface complexity risk Minor interface and/or interdependency with other entities, projects, programs, or services | 2
| Very low interface complexity risk Very little or infrequent interface or interdependency with other entities | 1
| Extremely low interface complexity risk No interface or interdependency with other entities, projects, programs, or services | 0
Risk 3: Procurement Complexity
Criteria and Weighting | Priority and Risk Level | Score | Evaluation Questions
Procurement Complexity: 20% The extent to which a project or program requires sophisticated, customised, or complex procurement methods (non-traditional), thereby increasing the need for a careful assessment and management of risk. Procurement complexity may also be influenced by the extent of agency experience and capability. For example, complex procurement methods may be used more commonly by some agencies and represent a lower procurement risk. | Very high procurement complexity risk Highly complex procurement model | 5 | Procurement Complexity indicators: • Will/could the project use a non-traditional (complex or customised) procurement method? • Does the agency have experience in the proposed procurement method? • Does the agency have a high-level of capability in the proposed procurement method? • Is the service contract likely to be >10 years? • Is the project dependent on input from an immature/inexperienced market segment?
| High procurement complexity risk Unconventional procurement model | 4
| Medium procurement complexity risk Some procurement complexity | 3
| Low procurement complexity Minor procurement complexity | 2
| Very low procurement complexity risk Business as usual procurement | 1
| Extremely low procurement complexity risk No procurement complexity | 0
Risk 4: Agency Capability
Criteria and Weighting | Priority and Risk Level | Score | Evaluation Questions
Agency Capability: 20% The extent to which the sponsor agency has demonstrated capability (skills and experience) or can access through recruitment or procurement the required capability in the development and/or delivery of the type of project or program proposed and/or its delivery strategy. | Very high agency capability risk No projects of this type previously delivered over the last 10 years | 5 | Agency Capability indicators: • Are the operations and outcomes of the project aligned to the agency's core business and strategic objectives? • Does the organisation have a successful track record of delivering initiatives of a similar scope and/or scale? • Has the organisation been established within the past 12 months? • Does the organisation have ongoing stable operations? • Does the organisation have an ongoing, stable source of funding? • Has the organisation been established for the purpose of delivering this project? • Has the organisation delivered a project that has been subject to a REAF Gateway Review? • Has the agency delivered a recurrent, capital or ICT project/program that has been subject to a recurrent, capital or ICT Gateway? • Will the agency be delivering this project in partnership with a more experienced delivery partner? • Will the agency be delivering this project in partnership with a less experienced delivery partner? • Does the agency have in-house capability to deliver the project, or will the agency be contracting/recruiting? • Does the agency have the capability to manage the ongoing activities of the project after the procurement stage?
| High agency capability risk Few projects of this type previously delivered over the last 10 years | 4
| Medium agency capability risk Several similar projects delivered over the last 5 years | 3
| Low agency capability risk Many similar projects delivered over the last 5 years | 2
| Very low agency capability risk Many similar projects delivered over the last 2 years | 1
| Extremely low agency capability risk Routine business as usual | 0
Risk 5: Criticality of Service
Criteria and Weighting | Priority and Risk Level | Score | Evaluation Questions
Criticality of Service: 15% The degree to which a project is essential to meet the needs of the community, enhances an essential service or addresses a deficiency which would otherwise have adverse impacts on an existing community or the growth of a new community. | Very high impact on an essential service Provides an enhancement or addresses an urgent and critical deficiency that could have a highly adverse impact on an essential service | 5 | Criticality of Service indicators: • Does the project involve a service that impacts an existing community? • Does the project involve a service that impacts the development or growth of a new community? • Is the fulfilment of a legislative requirement dependent on this project? • Is the delivery of a major Government policy initiative dependent on this project? • Is the project considered crucial to the operation of the agency? • Is the project considered crucial to the operation of Government? • Would the failure of the project have significant implications for the delivery of key public services? • Would the failure of the project have significant implications for regional, state, or national security? • Would the failure of the project have significant implications for the internal operations of the Delivery Agency?
| High impact on an essential service Provides an enhancement or addresses a deficiency that could have a significant impact on the delivery of an essential service | 4
| Medium impact on an essential service Provides an enhancement or addresses a deficiency that could have a moderate impact on the delivery of an essential service | 3
| Low impact on an essential service Provides an enhancement or addresses a deficiency that could have a minor impact on the delivery of an essential service | 2
| Very Low impact on an essential Services Provides an enhancement or addresses minor deficiency that could have a very low impact upon the delivery of an essential service | 1
| Extremely low impact on an essential service Not related to the delivery of an essential service | 0
Risk 6: Implementation Complexity
Criteria and Weighting | Priority and Risk Level | Score | Evaluation Questions
Implementation Complexity: 15% The extent to which the project’s success will depend on resolution in the agency of challenging industrial relations issues, significant re-organisation of functions or activities within the agency, relocation of functions or activities, changes of business processes and operational risk. | Very high implementation complexity There are a significantly high-level of unknowns and/or assumptions involved which may have a significant influence over successful implementation | 5 | Implementation Complexity indicators: • Does the project involve a significant organisation restructure to deliver services? • Does the project involve the relocation of existing functions or activities? • Does the project involve a significant change to business processes? • Does the project implementation affect existing industrial relations arrangements? • Does the project involve significant operational or sustainability risk?
| High implementation complexity There are a high-level of unknowns and/or assumptions which may influence over successful implementation | 4
| Medium implementation complexity There are a moderate level of unknowns and/or assumptions involved which may influence successful implementation | 3
| Low implementation complexity There are a low level of unknowns and/or assumptions involved which are unlikely to influence the success of implementation | 2
| Very low implementation complexity There are a low level of unknowns and/or assumptions involved which are highly unlikely to influence the success of implementation | 1
| Extremely low implementation complexity There are no unknowns and/or assumptions involved which will influence the success of implementation | 0

## Appendix 2
REAF Project Tier Weighted Risk Score Matrix | Risk Profile Criteria Weighting |  | REAF Qualitative Risk Profile Criteria
| Criteria | Weighting | Criteria | Priority and Risk level | Score
| Government priority | 15% | Government Priority | Very High Government priority | 5
| Interface complexity | 15% |  | High Government priority | 4
| Procurement complexity | 20% |  | Medium Government priority | 3
| Agency capability | 20% |  | Low Government priority | 2
| Criticality of Service | 15% |  | Very Low Government Priority | 1
| Implementation complexity | 15% |  | Extremely low Government priority | 0
|  |  | Interface Complexity | Very high interface complexity risk | 5
|  |  |  | High interface complexity risk | 4
|  |  |  | Medium interface complexity risk | 3
|  |  |  | Low interface complexity risk | 2
|  |  |  | Very low interface complexity risk | 1
Note: <$100M bracket also includes projects with an ETC under $100M but >$50M in any one year and any projects nominated by ERC, the agency or NSW Treasury. |  |  |  | Extremely low interface complexity risk | 0
|  |  | Procurement Complexity | Very high procurement complexity risk | 5
Application of Gateway Reviews by NSW Treasury |  |  |  | High procurement complexity risk | 4
|  |  |  | Medium procurement complexity risk | 3
|  |  |  | Low procurement complexity risk | 2
|  |  |  | Very low procurement complexity risk | 1
|  |  |  | Extremely low sourcing complexity risk | 0
|  |  | Agency Capability | Very high agency capability risk | 5
|  |  |  | High agency capability risk | 4
|  |  |  | Medium agency capability risk | 3
|  |  |  | Low agency capability risk | 2
|  |  |  | Very low agency capability risk | 1
|  |  |  | Extremely low agency capability risk | 0
|  |  | Criticality of Service | Very high impact on an essential service | 5
|  |  |  | High impact on an essential service | 4
|  |  |  | Medium impact on an essential service | 3
|  |  |  | Low impact on an essential service | 2
|  |  |  | Very Low impact on an Essential Services | 1
|  |  |  | Extremely low impact on an essential service | 0
|  |  | Implementation complexity | Very high implementation complexity risk | 5
|  |  |  | High implementation complexity risk | 4
|  |  |  | Medium implementation complexity risk | 3
|  |  |  | Low implementation complexity risk | 2
|  |  |  | Very low implementation complexity risk | 1
|  |  |  | Extremely low implementation complexity risk | 0

## Lists (hidden)
Government Priority (15%) |  | Stage at time of Project Registration | Registration Type: | Type of Recurrent Expenditure: | Funding Source: | Funding Approval Status: | Registration Status: | Tier | Responsible Minister | Department | Capital asset type | Project_program priority | Yes/No | Yes/No | Yes/No/Maybe | Yes/No/Developed | Yes-in place/Being developed/No | Health Checks | Frequency | Check |  | Risk Tier
- Please select - | - | - Please select - | - Please select - | - Please select - | - Please select - | - Please select - | - Please select - | - Please select - | - Please select - | - Please select - | 1. Infrastructure Project | State Budget Allocation | - Please select - | Yes | Yes | Yes | Yes-in place | None | Monthly | P | Very high change complexity risk |  | <$100M | $100M - $250M | $250M - $500M | >$500M
EXTREMELY LOW (Not a documented Government or agency priority) | 0 | Concept Development | Voluntary | Creating a new public entity (or new business unit within a public entity) | No Funding Source | None Approved | Draft | Tier 1 | Attorney General | Department of Climate Change, Energy, the Environment and Water | 2. Property Development | Strategic Plan | YES | No | No | No | Being developed | 1 | Quarterly | O | High change complexity risk | 0.0 - 2.0 | Tier 4 | Tier 4 | Tier 3 | Tier 2
VERY LOW (Agency priority in Agency Strategic Plan over the next 10 years) | 1 | Preliminary Business Case | Mandatory | Introducing a new service or policy | Agency Funded | Approved For Strategic Business Case | Ready for Approval | Tier 2 | Deputy Premier | Department of Communities and Justice | 3. Equipment | Election Commitment | NO | N/A | Possibly | Being Developed | No | 2 | None |  | Medium change complexity risk | 2.1 - 2.5 | Tier 4 | Tier 3 | Tier 2 | Tier 2
LOW (Priority Government project, and project will be commenced within the forward estimates period) | 2 | Business Case |  | Like to like renewal of existing policy/service that is due to lapse | Budget Funded - Approved | Approved For Detailed Business Case | Delivery Agency Approved | Tier 3 | Minister for Aboriginal Affairs and Treaty | Department of Customer Service | 4. ICT Project | Ministerial Commitment |  |  | N/A | N/A |  | 3 | Other |  | Lower change complexity risk | 2.6 - 3.0 | Tier 3 | Tier 2 | Tier 2 | Tier 2
MEDIUM (Priority Government project, and project will be fully operational within the next 3-4 years of the forward estimates period) | 3 | Pre-execution |  | Re-tender of existing services | Budget Funded - To Be Approved | Funding Approved | Submitted | Tier 4 | Minister for Agriculture | Department of Education | 5. Other capital expenditure | Legislation | [5 empty] | Greater than 3 |  |  | Very low change complexity risk | 3.1 - 4.0 | Tier 2 | Tier 2 | Tier 1 | Tier 1
HIGH (Priority Government project, and project will be fully operational within the next 1-2 years of the forward estimates period) | 4 | Tender Evaluation |  | Significant amendment/upgrade to an existing policy/program/service | Partly Budget Funded - Approved |  | Ready for Risk Review |  | Minister for Better Regulation and Fair Trading | Department of Enterprise, Investment and Trade |  | Other | [5 empty] | Unknown |  |  | Extremely low change complexity risk | 4.1 - 5.0 | Tier 1 | Tier 1 | Tier 1 | Tier 1
VERY HIGH (Priority Government project, and project will be fully operational within 12 months) | 5 | Pre-commissioning |  | Significant (non-routine) maintenance to an existing operating asset | Partly Budget Funded - To Be Approved |  |  |  | Minister for Building | Department of Planning, Housing and Infrastructure
|  | Implementation |  | Investment to enhance/extend agency capability |  |  |  |  | Minister for Climate Change | Department of Regional NSW
Interface Complexity (15%) |  | Closure |  | Grants |  |  |  |  | Minister for Corrections | Department of Transport
- Please select - | - |  |  | Outsourcing of a service |  |  |  |  | Minister for Customer Service and Digital Government | Independent Commission Against Corruption
EXTREMELY LOW (No interface or interdependency with other entities, projects, programs, or services) | 0 |  |  | Conducting a research program |  |  |  |  | Minister for Disability Inclusion | Independent Pricing and Regulatory Tribunal
VERY LOW (Very little or infrequent interface or interdependency with other entities) | 1 |  |  | Developing a strategy |  |  |  |  | Minister for Domestic Manufacturing and Government Procurement | Judicial Commission of New South Wales
LOW (Minor interface and/or interdependency with other entities, projects, programs, or services) | 2 |  |  | Responding to regulatory change |  |  |  |  | Minister for Education and Early Learning | Law Enforcement Conduct Commission |  |  | Funding Source |  |  |  | Example | Changetier | Yes | No
MEDIUM (Some interface and/or interdependency with other entities, projects, programs, or services) | 3 | [7 empty] | Minister for Emergency Services | Ministry of Health |  | Gate 0 - Project Justification | Budget funded-approved |  |  |  | selection 1 | Yes | Tier 1
HIGH (Frequent interface and/or interdependency with other entities, projects, programs, or services) | 4 | [7 empty] | Minister for Energy | New South Wales Electoral Commission |  | Gate 1 - Strategic Assessment | Budget funded-to be approved |  |  |  | selection 2 | No | Tier 2
VERY HIGH (Extensive interface and/or interdependence with other entities, projects, programs, or services) | 5 | [7 empty] | Minister for Families and Communities | Office of the Children's Guardian |  | Gate 2 - Business Case | Agency funded |  |  |  | selection 3 |  | Tier 3
[9 empty] | Minister for Finance | Office of the Director of Public Prosecutions |  | Gate 3 - Pre-Tender/Pre-execution | Partly Budget funded-approved | [5 empty] | Tier 4
Procurement Complexity (20%) | [8 empty] | Minister for Gaming and Racing | Ombudsman's Office |  | Gate 4 - Tender Evaluation | Partly Budget funded-to be approved
- Please select - | - | [7 empty] | Minister for Health | Other |  | Gate 5 - Pre-Commissioning | Other
EXTREMELY LOW (No procurement complexity) | 0 | [7 empty] | Minister for Heritage | Premier's Department |  | Gate 6 - Post-Implementation
VERY LOW (Business as usual procurement) | 1 | [7 empty] | Minister for Homelessness | Public Service Commission
LOW (Minor procurement complexity) | 2 | [7 empty] | Minister for Housing | The Cabinet Office
MEDIUM (Some procurement complexity) | 3 | [7 empty] | Minister for Industrial Relations | Treasury
HIGH (Unconventional procurement model) | 4 | [7 empty] | Minister for Industry and Trade
VERY HIGH (Highly complex procurement model) | 5 | [7 empty] | Minister for Innovation, Science and Technology
Minister for Jobs and Tourism
Agency Capability (20%) | [8 empty] | Minister for Lands and Property
- Please select - | - | [7 empty] | Minister for Local Government
EXTREMELY LOW (Routine business as usual) | 0 | [7 empty] | Minister for Medical Research
VERY LOW (Many similar projects delivered over the last 2 years) | 1 | [7 empty] | Minister for Mental Health
LOW (Many similar projects delivered over the last 5 years) | 2 | [7 empty] | Minister for Multiculturalism
MEDIUM (Several similar projects delivered over the last 5 years) | 3 | [7 empty] | Minister for Music and the Night-time Economy
HIGH (Few projects of this type previously delivered over the last 10 years) | 4 | [7 empty] | Minister for Natural Resources
VERY HIGH (No projects of this type previously delivered over the last 10 years) | 5 | [7 empty] | Minister for Planning and Public Spaces
Minister for Police and Counter-terrorism
Criticality of Service (15%) | [8 empty] | Minister for Regional Health
- Please select - | - | [7 empty] | Minister for Regional New South Wales
EXTREMELY LOW (Not related to the delivery of an essential service) | 0 | [7 empty] | Minister for Regional Transport and Roads
VERY LOW (Provides an enhancement or addresses minor deficiency that could have a very low impact upon the delivery of an essential service) | 1 | [7 empty] | Minister for Roads
LOW (Provides an enhancement or addresses a deficiency that could have a minor impact on the delivery of an essential service) | 2 | [7 empty] | Minister for Seniors
MEDIUM (Provides an enhancement or addresses a deficiency that could have a moderate impact on the delivery of an essential service) | 3 | [7 empty] | Minister for Skills, TAFE and Tertiary Education
HIGH (Provides an enhancement or addresses a deficiency that could have a significant impact on the delivery of an essential service) | 4 | [7 empty] | Minister for Small Business
VERY HIGH (Provides an enhancement or addresses an urgent and critical deficiency that could have a highly adverse impact on an essential service) | 5 | [7 empty] | Minister for Sport
Minister for the Arts
Implementation Complexity (15%) | [8 empty] | Minister for the Central Coast
- Please select - | - | [7 empty] | Minister for the Environment
EXTREMELY LOW (There are no unknowns and/or assumptions involved which will influence the success of implementation) | 0 | [7 empty] | Minister for the Hunter
VERY LOW (There are a low level of unknowns and/or assumptions involved which are highly unlikely to influence the success of implementation) | 1 | [7 empty] | Minister for the Illawarra and the South Coast
LOW (There are a low level of unknowns and/or assumptions involved which are unlikely to influence the success of implementation) | 2 | [7 empty] | Minister for the North Coast
MEDIUM (There are a moderate level of unknowns and/or assumptions involved which may influence successful implementation) | 3 | [7 empty] | Minister for the Prevention of Domestic Violence and Sexual Assault
HIGH (There are a high level of unknowns and/or assumptions which may influence over successful implementation) | 4 | [7 empty] | Minister for Transport
VERY HIGH (There are a significantly high level of unknowns and/or assumptions involved which may have a significant influence over successful implementation) | 5 | [7 empty] | Minister for Veterans
Minister for Water
Minister for Western New South Wales
Minister for Western Sydney
Minister for Women
Minister for Work Health and Safety
Minister for Youth
Minister for Youth Justice
Other
Premier
Special Minister of State
Treasurer